## Use Cases
# | Feature | Use case | Actor1 | Actor2 | Actor3 | Use case description | State
1 | Authentication | Login | User | Admin | Guest |  | Fixed
2 | Authentication | Logout | User | Admin |  |  | Fixed
3 | Authentication | Register | Guest |  |  |  | Fixed
4 | Authentication | Forgot password | User | Admin | Guest |  | Pending
5 | Manage user | Delete user | Admin |  |  |  | Pending
6 | Manage user | Search user | Admin |  |  |  | Pending
7 | Manage user | View User | Admin |  |  |  | Fixed
8 | Manage Profile | View Profile | User | Admin |  |  | Fixed
9 | Manage Profile | Change Password | User | Admin |  |  | Fixed
10 | Manage Profile | Update Profile | User | Admin |  |  | Fixed
11 | Captcha | Register
12 | Send Email | Register, Forgot password
13 | Phân quyền | Logout
14 | Search Jquerry ajax | Search user
15
16
17
18
19
20
21
22
23
24
25
26
27
28

## Product
# | Feature | Screen/Function | Screen/Function Details | In Charge | Status | RDS | Planned | Actual | Updated | Update Details
1 | Feature Name1 | Screen/Function Name1 | Mention the mapped UC and list out the detailed activities/functionalities that the user can do on the screen/function. See example below: View User Account List - Filter - Search - Sort - .. | HaTH | Done | II.1.3, III.5 | iter1 | iter1 | iter2
2 | User Access | User Login |  | KienNT | Done | II.1, III.8 | iter1 | iter1 | iter2
3 | User Access | Dashboaard |  | AnhPT | Doing |  | iter1 | iter1 | iter2
4 | Asset Management | Asset List |  | AnhPT | To Do |  | iter1 | iter1 | iter2
5 | … | [5 empty] | iter1 | iter1 | iter2
Note on G1: KienNT: The name of section in the RDS (requirement and design specification) document

## Iter1
# | Screen / Function | In Charge | Status | Notes
1 | Login Screen | Hung
2 | Register Screen | Vu
3 | Forgot password function | Hoang
4 | Logout function | Hung
5 | View profile Screen | Chien
6 | Search User Screen | Datts
7 | Change password function | Chien
8 | Update information function | Chien
9 | Captcha function | Datts
10 | Send email function | Datts
11 | Home Screen | Hung
12 | md5 hash encryption | Vu
13 | Session login user | Datts
14 | Authentication cookie | Datts
15 | DataAnnotations validate form | Vu
16 | Ajax jquerry search function | Datts
17 | Register complete Screen | Vu
18 | Forgot password Success Screen | Hoang
19 | Ajax jquerry captcha loader | Hung
20 | Detail User Screen | Datts
21 | Reset Password | Hoang
22 | List User | Chien

## Iter2
# | Screen / Function | In Charge | Status | Notes
1 | Screen/Function Name1 | KienNT | Done
2 | Screen/Function Name2 | VinhLX | To Do

## Iter3
# | Screen / Function | In Charge | Status | Notes
1 | Screen/Function Name1 | KienNT | Done
2 | Screen/Function Name2 | VinhLX | To Do